## Complexity Assessment
Complexity Assessment |  |  |  |  | Task
Level 1
<Project Name> |  |  |  |  | Level 2
TAC 216 Companion Guide Version: |  |  |  |  | Level 3
Document Version: |  |  |  |  | Level 4
Date Completed:
Completed by:
Project managers should thoroughly evaluate a project's potential risks and understand the project's complexity before starting it. This evaluation also helps identify issues before they can affect the project's successful completion. Use this Complexity Assessment to help you systematically evaluate the risks and complexities of this project.
Scope
Defining what is required is not always easy. Clearly defined deliverables, objectives, and scope minimize project risk. Evaluate and assess all scope risks, whether quantifiable or not.
How well are project scope and requirements defined? |  | Score | Notes
Clearly defined | 1
Some ambiguity | 5
Vague or undefined | 10
Schedule
Keeping to timelines and agreed critical paths is one of the most difficult situations that project managers face. Evaluate scheduling issues that may trigger a project risk.
What is the estimated time it will take to complete the project? |  | Score | Notes
3 months or less | 1
3 months - 1 year | 5
1 year or more | 10
Is there an internally or externally mandated deadline? |  | Score | Notes
No mandated deadline | 1
Internally mandated deadline | 5
Externally mandated deadline | 10
Budget
Accounting for the full cost of a project (e.g., materials, labor, vendors) provides a framework for ROI and insight into potential risks and associated project complexities. Consider all budget factors (including labor costs) that are needed for this project.
What is the total estimated cost (including payroll)? |  | Score | Notes
<$0.00> or less | 1
<$0.00> - <$0.00> | 5
<$0.00> - $999,999 | 10
$1,000,000 or more | LEVEL 4
Quality
Failing to deliver quality can negatively affect customer satisfaction and create unplanned expenses to fix or redo unsatisfactory work. Evaluate potential quality risks and complexities before beginning the project.
How defined are project team roles and responsibilities? |  | Score | Notes
Well defined roles and responsibilities | 1
Partially defined roles and responsibilities | 5
Undefined roles and responsibilities | 10
How available is the project team to work this project? |  | Score | Notes
Dedicated team available; minimal disruptions expected | 1
Partially dedicated or limited team; some disruptions expected | 5
Ad hoc or no clear team available; significant disruptions expected | 10
How knowledgeable is the project team with this type of project and/or the technology that will be used? |  | Score | Notes
Extensive knowledge and experience with this type of project or technology | 1
Some experience with this type of project or technology | 5
Little or no experience with this type of project or technology | 10
How involved are stakeholders? |  | Score | Notes
They define requirements, provide input to the schedule and accept deliverables | 1
Some input from surveys and they conduct final delivery testing | 5
No involvement or resistant to the project | 10
Organizational Impact
By definition, a project creates new and unique products or services which can impact processes or business units. Carefully evaluate the potential impact of this project on organizations and established processes.
How will this project impact current business processes? |  | Score | Notes
No change to business processes or work methods | 1
Some change to business processes or work methods | 5
Significant change to business processes or work methods | 10
How many A&M System members will this project impact or depend upon? |  | Score | Notes
Systems Offices department | 1
Multiple SO departments, or a single A&M System member | 5
Multiple A&M System members | 10
All A&M System members | LEVEL 4
Other Risk Considerations
Assess the project against the following categories important to A&M System members.
Other Risks (Score all that apply) |  | Score | Notes
Includes managed data (FERPA, HIPAA, PCI, etc.) | 10
Impacts other critical systems or services | 10
Requires vendor involvement | 10
Requires contingent or contract labor | 10
Has high external visibility | 10
Creates a conflict with previously established A&M System Executive IT Council decisions | LEVEL 4
Project Complexity and Risk Factor Category Scores
Clarity of Scope/Requirements | 0 | Project Team Knowledge |  | 0
Project Length | 0 | Stakeholder Involvement |  | 0
Project Deadline | 0 | Business Process Impact |  | 0
Estimated Costs | 0 | System Member Impact |  | 0
Project Team Roles/Responsibilities | 0 | Other Risks |  | 0
Project Team Availability | 0 | Total Point Value |  | 0
Overall Project Complexity and Risk Score
Task (9 - 25) |  | Level 3 Project (76 - 100, but no Level 4 factors)
Level 1 Project (26 - 50) |  | Level 4 Project (> 100 or one or more Level 4 factors)
Level 2 Project (51 - 75)
If your project scores at or will be managed at a Level 4 at anytime, please refer to the "Project Classification" section and Appendix B for Internal Audit guidelines.

## Combined Checklist
[5 empty] | Project: | <Project Name>
[5 empty] | Score: | 0
[5 empty] | Level: | Task
[5 empty] | Level Claimed: | <PULL DOWN>
Justification:
Initiating Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Location
Develop Business Case |  |  | X | X
Project Overview
Business Need |  |  | X | X
Business Goals/Objectives |  |  | X | X
Recommendation |  |  | X | X
Justification and Impact |  |  | X | X
Customer |  |  | X | X
Project Manager Involvement |  |  | X | X
Projected Project Budget and Funding Source |  |  | X | X
Assumptions |  |  | X | X
Limitations/Constraints |  |  | X | X
Risks |  |  | X | X
Project Evaluation
Strategic Alignment |  |  | X | X
Business Value |  |  | X | X
Institution/Agency Priority |  |  | X | X
Develop Charter
Project Information
Project Name | X | X | X | X
Performing Organization | X | X | X | X
Project Overview
What are you trying to achieve? | X | X | X | X
Why is this important? How does it align to business goals and objectives? | X | X | X | X
How will success be measured? Financial/Quantitative - are you retiring a piece of hardware, software, recovering a license cost? Business Impact - are you expanding a workflow, bringing new functionality to end users, including more end users in a workflow? | X | X | X | X
Scope
What are you going to do? | X | X | X | X
What is explicitly not going to be included? | X | X | X | X
Stakeholders
Project Sponsor(s) | X | X | X | X
Project Manager | X | X | X | X
Other key stakeholders | X | X | X | X
Schedule, budget, and resources
Develop a rough schedule | X | X | X | X
Develop a rough budget | X | X | X | X
Define funding and oversight authority |  |  | X | X
Identify key resources, roles, and responsibilities | X | X | X | X
Risk and quality considerations
What can go wrong? | X | X | X | X
Does the project involve confidential information? | X | X | X | X
Is the project subject to System Governance or Internal Audit oversight? |  |  | X | X
Assumptions and Constraints
Describe any assumptions about the events or circumstances you are expecting to occur during the project | X | X | X | X
Describe limitations or restrictions that may impact execution of the project | X | X | X | X
Prioritize the triple constraints (scope, time, cost) | X | X | X | X
Who will support/operate the result when the project ends? |  | X | X | X
Approve Charter for planning | X | X | X | X
Identify stakeholders | X | X | X | X
Create document repository (See Appendix D - Project Document Management) and collaboration environment | X | X | X | X
Planning Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Location
Prepare a baseline Project Plan Address the following topics in the appropriate detail
Scope
Develop a statement of scope | X | X | X | X
Develop a list of requirements | X | X | X | X
Develop a list of deliverables | X | X | X | X
Develop a work breakdown structure * Include Change Management activities and tasks as appropriate (See Appendix A - Organizational Change Management) |  |  | X | X
Schedule
Update the schedule | X | X | X | X
Provide the level of uncertainty for estimates |  | X | X | X
Document work assignments | X | X | X | X
Budget and Oversight
Update the budget | X | X | X | X
Provide the level of uncertainty for estimates |  | X | X | X
Who will approve the budget? |  |  | X | X
Develop the procurement plan | X | X | X | X
Resources, roles, and responsibilities
Develop a RACI (Responsible, Accountable, Consulted, and Informed) chart for project milestones | X | X | X | X
Risks
Identify and analyze risks | X | X | X | X
Plan for risk prevention and response | X | X | X | X
Formalize the risk register |  |  | X | X
Quality
Identify applicable quality standards | X | X | X | X
Define quality assurance and control processes |  |  | X | X
Communication
Develop project communication plan - identify who needs to know what and when and how information will be disseminated | X | X | X | X
Stakeholder Register
Analyze current and desired level of engagement for key stakeholders |  |  | X | X
Analyze impacts to stakeholders |  |  | X | X
Assumptions and Constraints
Update assumptions and constraints | X | X | X | X
Change Control
Define how changes to scope, schedule and budget will be requested | X | X | X | X
Identify who will receive requests and make decisions | X | X | X | X
Plan frequency of change control board or project steering committee meetings |  |  | X | X
Deployment, Stabilization and Transition to Operations (See Appendix B - Deployment)
Define the project deployment approach and processes | X | X | X | X
Plan how the result will be transitioned to operational status |  | X | X | X
Describe project support requirements - who will be responsible for meeting these requirements? | X | X | X | X
Develop Executing, Monitoring & Controlling templates Change Log Status Report Lessons Learned Issues Log | X | X | X | X
Approve Plan for Executing | X | X | X | X
Executing Monitoring & Controlling Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Location
Execute, Monitor, and Control the Project
Build and train the project team | X | X | X | X
Ensure key stakeholders are familiar with the Project Plan: -Project goals and objectives -Project budget and schedule -Project team roles and responsibilities, and collaboration methods/tools -Critical success factors and deliverables acceptance criteria -Risk and issue management processes -Project communication strategy -Change control processes | X | X | X | X
Critical success factors and deliverables acceptance criteria | X | X | X | X
Risk and issue management processes | X | X | X | X
Project communication strategy | X | X | X | X
Change control processes | X | X | X | X
Perform project work including quality assurance and procurement activities | X | X | X | X
Track progress of actual performance against projected performance and analyze reasons for any variations | X | X | X | X
Manage project communications and stakeholder engagement | X | X | X | X
Capture and communicate requested and approved changes | X | X | X | X
Maintain the Project Log: -Review and update the Issues Log -Review and update the Risk Register -Review and update Action Items -Update the Change Log | X | X | X | X
Make necessary updates to the Project Plan | X | X | X | X
For complex deployments, develop and execute a deployment plan that also addresses communication |  |  | X | X
Obtain signoff on project deliverables | X | X | X | X
Closing Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Location
Obtain final acceptance of project completion | X | X | X | X
Close out the project
Deployment and transition to operations
Notify users | X | X | X | X
Develop end-user and operational documentation | X | X | X | X
Transfer knowledge to operational staff and service desk | X | X | X | X
Update information resources management system/configuration management database |  |  | X | X
Update Service Catalog/IT Services list and business processes | X | X | X | X
Establish product/service governance, if applicable |  |  | X | X
Release new products/services | X | X | X | X
Stabilization
Identify and address any open issues on the project | X | X | X | X
Finalize project backing |  | X | X | X
Close out procurement relationship
Finalize any open claims | X | X | X | X
Update records to reflect final results | X | X | X | X
Evaluate and document vendor performance | X | X | X | X
Conduct lessons learned for continuous improvement
Complete Compliance Validation Check list (See Appendix E - TAC 216 Compliance Validation Checklist) | X | X | X | X
Project management processes |  | X | X | X
Change management processes |  | X | X | X
Product/service development processes |  | X | X | X
Archive project documents (See Appendix D - Project Document Management) | X | X | X | X

## Initiating
[5 empty] | Project: | <Project Name>
[5 empty] | Score: | 0
[5 empty] | Level: | Task
[5 empty] | Level Claimed: | <PULL DOWN>
[5 empty] | Justification: | 0
Initiating Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Location
Develop Business Case |  |  | X | X
Project Overview
Business Need |  |  | X | X
Business Goals/Objectives |  |  | X | X
Recommendation |  |  | X | X
Justification and Impact |  |  | X | X
Customer |  |  | X | X
Project Manager Involvement |  |  | X | X
Projected Project Budget and Funding Source |  |  | X | X
Assumptions |  |  | X | X
Limitations/Constraints |  |  | X | X
Risks |  |  | X | X
Project Evaluation
Strategic Alignment |  |  | X | X
Business Value |  |  | X | X
Institution/Agency Priority |  |  | X | X
Develop Charter
Project Information
Project Name | X | X | X | X
Performing Organization | X | X | X | X
Project Overview
What are you trying to achieve? | X | X | X | X
Why is this important? How does it align to business goals and objectives? | X | X | X | X
How will success be measured? Financial/Quantitative - are you retiring a piece of hardware, software, recovering a license cost? Business Impact - are you expanding a workflow, bringing new functionality to end users, including more end users in a workflow? | X | X | X | X
Scope
What are you going to do? | X | X | X | X
What is explicitly not going to be included? | X | X | X | X
Stakeholders
Project Sponsor(s) | X | X | X | X
Project Manager | X | X | X | X
Other key stakeholders | X | X | X | X
Schedule, budget, and resources
Develop a rough schedule | X | X | X | X
Develop a rough budget | X | X | X | X
Define funding and oversight authority |  |  | X | X
Identify key resources, roles, and responsibilities | X | X | X | X
Risk and quality considerations
What can go wrong? | X | X | X | X
Does the project involve confidential information? | X | X | X | X
Is the project subject to System Governance or Internal Audit oversight? |  |  | X | X
Assumptions and Constraints
Describe any assumptions about the events or circumstances you are expecting to occur during the project | X | X | X | X
Describe limitations or restrictions that may impact execution of the project | X | X | X | X
Prioritize the triple constraints (scope, time, cost) | X | X | X | X
Who will support/operate the result when the project ends? |  | X | X | X
Approve Charter for planning | X | X | X | X
Identify stakeholders | X | X | X | X
Create document repository (See Appendix D - Project Document Management) and collaboration environment | X | X | X | X

## Planning
[5 empty] | Project: | <Project Name>
[5 empty] | Score: | 0
[5 empty] | Level: | Task
[5 empty] | Level Claimed: | <PULL DOWN>
[5 empty] | Justification: | 0
Planning Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Location
Prepare a baseline Project Plan Address the following topics in the appropriate detail
Scope
Develop a statement of scope | X | X | X | X
Develop a list of requirements | X | X | X | X
Develop a list of deliverables | X | X | X | X
Develop a work breakdown structure * Include Change Management activities and tasks as appropriate (See Appendix A - Organizational Change Management) |  |  | X | X
Schedule
Update the schedule | X | X | X | X
Provide the level of uncertainty for estimates |  | X | X | X
Document work assignments | X | X | X | X
Budget and Oversight
Update the budget | X | X | X | X
Provide the level of uncertainty for estimates |  | X | X | X
Who will approve the budget? |  |  | X | X
Develop the procurement plan | X | X | X | X
Resources, roles, and responsibilities
Develop a RACI (Responsible, Accountable, Consulted, and Informed) chart for project milestones | X | X | X | X
Risks
Identify and analyze risks | X | X | X | X
Plan for risk prevention and response | X | X | X | X
Formalize the risk register |  |  | X | X
Quality
Identify applicable quality standards | X | X | X | X
Define quality assurance and control processes |  |  | X | X
Communication
Develop project communication plan - identify who needs to know what and when and how information will be disseminated | X | X | X | X
Stakeholder Register
Analyze current and desired level of engagement for key stakeholders |  |  | X | X
Analyze impacts to stakeholders |  |  | X | X
Assumptions and Constraints
Update assumptions and constraints | X | X | X | X
Change Control
Define how changes to scope, schedule and budget will be requested | X | X | X | X
Identify who will receive requests and make decisions | X | X | X | X
Plan frequency of change control board or project steering committee meetings |  |  | X | X
Deployment, Stabilization and Transition to Operations (See Appendix B - Deployment)
Define the project deployment approach and processes | X | X | X | X
Plan how the result will be transitioned to operational status |  | X | X | X
Describe project support requirements - who will be responsible for meeting these requirements? | X | X | X | X
Develop Executing, Monitoring & Controlling templates Change Log Status Report Lessons Learned Issues Log | X | X | X | X
Approve Plan for Executing | X | X | X | X

## EM&C
[5 empty] | Project: | <Project Name>
[5 empty] | Score: | 0
[5 empty] | Level: | Task
[5 empty] | Level Claimed: | <PULL DOWN>
[5 empty] | Justification: | 0
Executing Monitoring & Controlling Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Location
Execute, Monitor, and Control the Project
Build and train the project team | X | X | X | X
Ensure key stakeholders are familiar with the Project Plan: -Project goals and objectives -Project budget and schedule -Project team roles and responsibilities, and collaboration methods/tools -Critical success factors and deliverables acceptance criteria -Risk and issue management processes -Project communication strategy -Change control processes | X | X | X | X
Critical success factors and deliverables acceptance criteria | X | X | X | X
Risk and issue management processes | X | X | X | X
Project communication strategy | X | X | X | X
Change control processes | X | X | X | X
Perform project work including quality assurance and procurement activities | X | X | X | X
Track progress of actual performance against projected performance and analyze reasons for any variations | X | X | X | X
Manage project communications and stakeholder engagement | X | X | X | X
Capture and communicate requested and approved changes | X | X | X | X
Maintain the Project Log: -Review and update the Issues Log -Review and update the Risk Register -Review and update Action Items -Update the Change Log | X | X | X | X
Make necessary updates to the Project Plan | X | X | X | X
For complex deployments, develop and execute a deployment plan that also addresses communication |  |  | X | X
Obtain signoff on project deliverables | X | X | X | X

## Closing
[5 empty] | Project: | <Project Name>
[5 empty] | Score: | 0
[5 empty] | Level: | Task
[5 empty] | Level Claimed: | <PULL DOWN>
Justification:
Closing Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Location
Obtain final acceptance of project completion | X | X | X | X
Close out the project
Deployment and transition to operations
Notify users | X | X | X | X
Develop end-user and operational documentation | X | X | X | X
Transfer knowledge to operational staff and service desk | X | X | X | X
Update information resources management system/configuration management database |  |  | X | X
Update Service Catalog/IT Services list and business processes | X | X | X | X
Establish product/service governance, if applicable |  |  | X | X
Release new products/services | X | X | X | X
Stabilization
Identify and address any open issues on the project | X | X | X | X
Finalize project backing |  | X | X | X
Close out procurement relationship
Finalize any open claims | X | X | X | X
Update records to reflect final results | X | X | X | X
Evaluate and document vendor performance | X | X | X | X
Conduct lessons learned for continuous improvement
Complete Compliance Validation Check list (See Appendix E - TAC 216 Compliance Validation Checklist) | X | X | X | X
Project management processes |  | X | X | X
Change management processes |  | X | X | X
Product/service development processes |  | X | X | X
Archive project documents (See Appendix D - Project Document Management) | X | X | X | X

## UTILITY (hidden)
Dropdown menu
Task
Level 1
Level 2
Level 3
Level 4