## Original (hidden)
Option 1 and 2 Timeline, Action Items, Forms and Reports
| Option 1 | Option 2
Date | Action Item | Action Item | Business Objects Reports | Workday Reports | Form
Friday, May 8 | Submit Merit Configuration Worksheet |  |  |  | Merit Configuration Worksheet
| Submit Merit Partner SOR to Sri Kamarthi to add role to new users |  |  |  | Statement of Responsibility
| Update access to users for Position Budgeting Application |  |  |  | SSO Statement of Responsibility
Monday, May 11 | Snapshot from Workday loaded to PBA
Tuesday, May 12 - Friday, August 7 | Continuously update PBA to match Workday for: (New Hires, Terminations, Promotions, Transfers, Org Structure Changes) |  | Actions Needed in PBA | Compensation Changes
Monday, June 1 | Earliest launch for Workday Merit | PBA available per request
Option 2
Monday, June 1 - Monday, August 3 |  | Upload fund blind salary increase .csv file to PBA or enter % increases manually | Report
|  | Schedule Prep 901's to run daily | HCM Prep 901
Update costing allocations in PBA
|  | Correct costing errors posted to Sandbox | Costing Allocation Errors
|  | Optional: Run FBAU584/672 | Board Budget to Current Submitted Budget
|  | Reconcile PBA salaries to 589/599 | Prep to FAMIS Salary Comparison
Monday, August 3 |  | PBA closed to departments
Tuesday, August 4 |  | Workday Merit Launches
Tuesday, August 4 - Friday, August 7 |  | PBA Merit EIB file loaded to Workday Merit
|  | Verify Workday Merit = PBA; correct errors | HCM Prep to Workday Merit Increase Report
Friday, August 7 |  | PBA closed to Central Admin
Monday, August 10 - Monday, August 17 |  | Update Workday Merit as needed
Option 1
Monday, June 1 - Wednesday, July 15 | Merit Planners/Managers complete Workday Merit Entry
Thursday, July 16 | Workday Merit upload to PBA |  | Workday Merit Entry
Friday, July 17 - Friday, August 7 | Update costing allocations in PBA
| Correct costing Errors identified in Sandbox |  | Costing Allocation Errors
| Optional: FBAU584/672 |  | Board Budget vs. Current Submitted Budget
| Run Daily Prep 901's |  | HCM Prep 901's
| Reconcile PBA salaries to 589/599 salaries |  | Prep to FAMIS Salary Comparison
Friday, August 7 | PBA closed to departments
Monday, August 10- Monday, August 17 | PBA Central Admin finalize entry; Correct costing allocation errors |  | Costing Allocation Errors
Monday, August 17 | Workday Merit Finalized
Monday, August 24 | Final PBA Snapshot |  | Salary Budget
Thursday, August 27 | Costing allocations post to Workday
Friday, August 28 | Mark FAMIS Budget with a "D"

## Option 1
Option 1 Timeline, Action Items, and Resources
WHEN / WHAT / WHO |  |  |  | ACTION | RESOURCES
Dates | App | POC | Initiator | Option 1 | Forms/Reports/Templates | Purpose:
March | FAMIS | J. Eisenrich / K. Holt | Member | Review accounts (map codes, SA flags, etc.) Members submit FBAU588 Prodcard | Account Attribute Report (EDW00234) FBAU588 Prodcard Template | EDW00234 - current FY account attributes with budget module account attributes (patterns, SA Flags, No Feed/Budget) To be used to assign budget patterns and flags to accounts in FAMIS budget module
Monday, April 3 | PBA | D. Kessner / K. Holt | SO | Initial snapshot from Workday loaded to PBA for Phase I Budget | EDW00016 - HCM Prep 901 Excel by SA Org | Report can be used to estimate lump sum salaries/estimated benefits
Tuesday, April 4 | FAMIS | J. Eisenrich | SO | FAMIS runs the YU800 to start the budget process
Monday, April 10 | FAMIS | J. Eisenrich | Member | Member patterns due - SO to review before member is unlocked
Thursday, April 20 | FAMIS | J. Eisenrich | SO | FAMIS budget module opened to members
Prior to May 1 | PBA | Kelli Holt | Member | Review Workstation Preferences/Benefit Values | FAMIS Enhancement Request | Send FAMIS Enhancement Request to officially update ACAP and UCI Rates; Send email to kholt@tamus.edu and j-eisenrich to update rates in PBA
Monday, May 1 | PBA | Kelli Holt | Member | Begin running (3x a day) FBAR670, 671 and 665 | FBAR670, 671 and 665 reports available in Laserfiche
Friday, May 5 - Monday, May 29 | WD | Sri Kamarthi | Workday | Submit Merit Configuration Worksheet 3-weeks prior to launch | Merit Configuration Worksheet | Needed to configure Workday Merit Module
|  |  |  | Submit Merit Partner SOR to Sri Kamarthi to add role to new users | Merit Partner SOR | Needed for Workday Merit Access
|  |  |  | Update access to users for Position Budgeting Application | SSO SOR | Needed for PBA Access
Wednesday, May 10 | PBA | D. Kessner / K. Holt | System Offices | May 10th Snapshot from Workday loaded to PBA; Load costing to sandbox to identify errors early | EDW00212 Prep Cost Allocation Errors | HCM Prep Reports available with May 10th snapshot
Monday, May 22 - Sunday, Aug 20 | PBA | Kelli Holt | Member | PBA available upon request; Check for Positions on Default Members continuously update PBA to match Workday for: (New Hires, Terminations, Promotions, Transfers) | EDW00179 HCM Prep Template by Adloc Mbr EDW00230 Actions Needed in PBA EDW00214 Differences Comparing PBA to Workday WKDY - Compensation Changes | EDW00214 - another report to identify differences between PBA/WKDY; Compensation Changes - To help identify comp and other changes effective 9/1, which will need to be updated in PBA
Monday, May 29 | WD | Sri Kamarthi | SO | Earliest launch for Workday Merit / End of 88th Regular Session
Monday, June 5- Monday, July 17 | WD | Sri Kamarthi | Member | Merit Planners/Managers complete Workday Merit Entry and Submit
Friday, June 16 | FAMIS | J. Eisenrich / K. Holt | Member | Budget and Supplemental items due to System Offices | See SO Budget Office Teams member channel | Narrative, GR Recon, Estimated Beginning Balance, Retention Plant (SO Budget Office - General channel)
Monday, July 17 | FAMIS | J. Eisenrich | SO | Budget marked as "Board Approved"
July - TBD | FAMIS | J. Eisenrich | Member | Due: Programmatic Budget Review Presentations / Board Agenda Items to Board Office
Monday, July 17 - Monday, Aug 14 Start and end dates are member specific | PBA | Kelli Holt | Member | *Workday Merit upload to PBA-multiple uploads via .csv are possible | EDW00217 HCM Workday Merit Entry Upload to PBA; HCM Prep (PBA)<>Workday Merit Entry (in dev) | Business Objects report that includes Position ID, UIN, % Increase for Merit; % Increase for Promotion and % Increase for Other Adjustments. File will be used to populate PBA, if there is a match of Position ID/UIN combination in both applications.
* Update costing allocations in PBA
|  |  |  | * Correct costing Errors identified in Sandbox | EDW00212 Prep Cost Allocation Errors | Identifies costing allocations that will not load to Workday due to various reasons
|  |  |  | * Run Prep 901 | EDW00016 HCM Prep 901 by Source Mbr | Business Objects Report: To verify PBA entry is correct; provides salary totals by SL-SA
| FAMIS | Kelli Holt | Member | * Optional: Run FAMIS FBAU584/672
|  |  |  | * Optional: Reconcile PBA salaries to 589/599 salaries | EDW HCM Prep (PBA) to FAMIS Salary Comparison | Business Objects Report: Identifies salaries on costing allocations with no submitted budget in FAMIS; Unique to each member
Friday, Jul 28 | WD | Sri Kamarthi | Member | Request One-Time (OT) Merit EIB's from Sri Kamarthi | OT Merit EIB
August - TBD |  | J. Eisenrich | Member | FY 2024 Programmatic Budget Reviews with Board
Monday, July 31 - Friday, Aug 18 | WD | Sri Kamarthi | Member | Submit completed One-Time (OT) Merit EIB requests to Sri Kamarthi
Monday, Aug 7 | PBA | Kelli Holt | Member | Email Kelli Holt to request PBA closed to departments (date determined by member)
Tuesday, Aug 8 - Monday, Aug 21 | WD / PBA | S. Kamarthi / K. Holt | Member | Central Admin continue manually updating Workday Merit and PBA as needed | Workday-Merit Awards on Hold Audit; Costing Error Reports; EDW00214 - Differences between PBA/ Workday | Workday report that identifies merits on hold because of an in-progress Business Process; PBA report that identifies costing allocations that will not load to Workday; BO report that identifies differences between PBA and Current Workday
Wednesday, Aug 16 - Thursday, Aug 17 |  | J. Eisenrich | SO | FY 2024 Budget presented to the Board for approval
Monday, Aug 21 | PBA / WD | K. Holt / S. Kamarthi | System Offices | PBA Closed to Central Admin Workday Merit Finalized Systemwide
Wednesday, Aug 23 | PBA | D. Kessner / K. Holt | System Offices | Final PBA Snapshot | HCM Prep - Salary Budget | FY 2023 Salary Budget - should match FAMIS "Done" budget
Thursday, Aug 24 | PBA | D. Kessner / K. Holt | System Offices | Costing allocations post to Workday
Friday, Aug 25 | FAMIS | Jarrett Eisenrich | System Offices | Mark FAMIS Budget with a "D"

## Options 2
Option 2 Timeline, Action Items, and Resources
WHEN / WHAT / WHO |  |  |  | ACTION | RESOURCES
Dates | App | POC | Initiator | Option 2 | Forms/Reports/Templates | Purpose:
March | FAMIS | J. Eisenrich / K. Holt | Member | Review accounts (map codes, SA flags, etc.) Members submit FBAU588 Prodcard | Account Attribute Report (EDW00234) FBAU588 Prodcard Template | EDW00234 - current FY account attributes with budget module account attributes (patterns, SA Flags, No Feed/Budget) To be used to assign budget patterns and flags to accounts in FAMIS budget module
Monday, April 3 | PBA | D. Kessner / K. Holt | SO | Initial snapshot from Workday loaded to PBA for Phase I Budget | EDW00016 - HCM Prep 901 Excel by SA Org | Report can be used to estimate lump sum salaries/estimated benefits
Tuesday, April 4 | FAMIS | J. Eisenrich | SO | FAMIS runs the YU800 to start the budget process
Monday, April 10 | FAMIS | J. Eisenrich | Member | Member patterns due - SO to review before member is unlocked
Thursday, April 20 | FAMIS | J. Eisenrich | SO | FAMIS budget module opened to members
Prior to May 1 | PBA | Kelli Holt | Member | Review Workstation Preferences/Benefit Values | FAMIS Enhancement Request | Send FAMIS Enhancement Request to officially update ACAP and UCI Rates; Send email to budget@tamus.edu to update rates in PBA
Monday, May 1 | FAMIS | Kelli Holt | Member | Begin running (3x a day) FBAR670, 671 and 665 | FBAR670, 671 and 665 reports available in Laserfiche | Send FAMIS Enhancement Request to officially update ACAP and UCI Rates; Send email to budget@tamus.edu to update rates in PBA
Friday, May 5 - Monday, May 29 | WD | Sri Kamarthi | Workday | Submit Merit Configuration Worksheet 3-weeks prior to launch | Merit Configuration Worksheet | Needed to configure Workday Merit Module
|  |  |  | Submit Merit Partner SOR to Sri Kamarthi to add role to new users | Merit Partner SOR | Needed for Workday Merit Access
|  |  |  | Update access to users for Position Budgeting Application | SSO SOR | Needed for PBA Access
Wednesday, May 10 | PBA | D. Kessner / K. Holt | System Offices | May 10th Snapshot from Workday loaded to PBA; Load costing to sandbox to identify errors early | EDW00212 Prep Cost Allocation Errors | HCM Prep Reports available with May 10th snapshot
Monday, May 22 - Sunday, Aug 20 | PBA | Kelli Holt | Member | PBA available upon request; Check for Positions on Default Members continuously update PBA to match Workday for: (New Hires, Terminations, Promotions, Transfers) | EDW00179 HCM Prep Template by Adloc Mbr EDW00230 Actions Needed in PBA EDW00214 Differences Comparing PBA to Workday WKDY - Compensation Changes | EDW00214 - another report to identify differences between PBA/WKDY; Compensation Changes - To help identify comp and other changes effective 9/1, which will need to be updated in PBA
Monday, May 29 | WD | Sri Kamarthi | System Offices | Earliest launch for Workday Merit / End of 88th Regular Session
Tuesday, May 11 - Monday, May 30 | PBA | Kelli Holt | Member | Email Kelli Holt to request the Departmental Salary Increase Template | Departmental Salary Increase Template (available upon request)
Friday, June 16 | FAMIS | J. Eisenrich / K. Holt | Member | Budget and Supplemental items due to System Offices | See SO Budget Office Teams member channel | Narrative, GR Recon, Estimated Beginning Balance, Retention Plant (SO Budget Office - General channel)
Monday, July 17 | FAMIS | J. Eisenrich | Member | Budget marked as "Board Approved"
July - TBD | FAMIS | J. Eisenrich | Member | Due: Programmatic Budget Review Presentations / Board Agenda Items to Board Office
Monday, June 26 - Monday, July 31 (Start and end times are member specific) | PBA | Kelli Holt | Member | At member discretion, upload salary increase template .csv file to PBA or enter % increases manually in PBA
* Update costing allocations in PBA
|  |  |  | * Schedule Prep 901's to run or refresh manually | EDW00016 Prep 901 by Source Mbr | Business Objects Report: used to verify PBA entry is correct; provides salary totals by SL-SA
|  |  |  | * Correct costing errors posted to Sandbox | EDW00212 Prep Cost Allocation Errors | Identifies costing allocations that will not load to Workday due to various reasons
Monday, July 10 - Monday, Aug 14 | FAMIS | FAMIS Help | Member | Optional: Run FAMIS FBAU584/672
| EDW | Kelli Holt | Member | Optional: Reconcile PBA salaries to 589/599 | HCM Prep (PBA) to FAMIS Budget Salary Comparison | Business Objects Report: Identifies salaries on costing allocations with no submitted budget in FAMIS; Unique to each member; Email Kelli Holt if interested
Friday, Jul 28 | WD | Sri Kamarthi | Member | Request One-Time (OT) Merit EIB's from Sri Kamarthi | OT Merit EIB
Monday, July 31 - Friday, Aug 18 | WD | Sri Kamarthi | Member | Submit completed One-Time (OT) Merit EIB requests to Sri Kamarthi
August - TBD |  | J. Eisenrich | Member | FY 2024 Programmatic Budget Reviews with Board
Monday, July 31 - Tuesday, Aug 1 | PBA / WD | S. Kamarthi / K. Holt | Member | Test PBA EIB load to WKDY sandbox per Member request to identify and address errors | Request EIB to load costing allocations in WD Sandbox - do this on a Monday; EIB Posting Errors in Sandbox | Exact process TBD
Wednesday, Aug 2 - Monday, Aug 14 | WD | S. Kamarthi | Member | Launch Workday Merit and Load EIB (1X/member); Date of EIB upload = member's merit launch date
| EDW | Kelli Holt | Member | Run exceptions report to identify differences between PBA and Workday Merit | HCM Prep <> Workday Merit Report (in dev)
| WD / PBA | S. Kamarthi / K. Holt | Member | Correct differences until PBA and WKDY merit closes |  | Business Objects report that compares the merit entry in PBA to what was loaded via EIB from PBA to Workday Merit
Monday, Aug 7 |  |  |  | PBA closed to departments (date determined by member)
Tuesday, Aug 8 - Monday, Aug 21 | WD / PBA | S. Kamarthi / K. Holt | Member | Central Admin continue manually updating Workday Merit and PBA as needed | Workday-Merit Awards on Hold Audit; EDW00212 Prep Cost Allocation Errors EDW00214 Differences when Comparing PBA to WD EDW00230 Actions Needed in PBA | Workday report that identifies merits on hold because of an in-progress Business Process; PBA report that identifies costing allocations that will not load to Workday; BO report that identifies differences between PBA and Current Workday
Wednesday, Aug 16 - Thursday, Aug 17 |  | J. Eisenrich | SO | FY 2024 Budget presented to the Board for approval
Monday, Aug 21 | WD / PBA | S. Kamarthi / K. Holt | System Offices | PBA Closed to Central Admin/ Workday Merit Finalized Systemwide
Wednesday, Aug 23 | PBA | D. Kessner / K. Holt | System Offices | Final PBA Snapshot | HCM Prep - Salary Budget | FY 2022 Salary Budget - should match FAMIS "Done" budget
Thursday, Aug 24 | PBA | D. Kessner / K. Holt | System Offices | Costing allocations post to Workday
Friday, Aug 25 | FAMIS | Jarrett Eisenrich | System Offices | Mark FAMIS Budget with a "D"

## Options 3
Option 3 Timeline, Action Items, and Resources
WHEN / WHAT / WHO |  |  |  | ACTION | RESOURCES
Dates | App | POC | Initiator | Option 3 | Forms/Reports/Templates | Purpose:
March | FAMIS | J. Eisenrich / K. Holt | Member | Review accounts (map codes, SA flags, etc.) Members submit FBAU588 Prodcard | Account Attribute Report (EDW00234) FBAU588 Prodcard Template | EDW00234 - current FY account attributes with budget module account attributes (patterns, SA Flags, No Feed/Budget) To be used to assign budget patterns and flags to accounts in FAMIS budget module
Monday, April 3 | PBA | D. Kessner / K. Holt | SO | Initial snapshot from Workday loaded to PBA for Phase I Budget | EDW00016 - HCM Prep 901 Excel by SA Org | Report can be used to estimate lump sum salaries/estimated benefits
Tuesday, April 4 | FAMIS | J. Eisenrich | SO | FAMIS runs the YU800 to start the budget process
Monday, April 10 | FAMIS | J. Eisenrich | Member | Member patterns due - SO to review before member is unlocked
Thursday, April 20 | FAMIS | J. Eisenrich | SO | FAMIS budget module opened to members
Prior to May 1 | PBA | Kelli Holt | Member | Review Workstation Preferences/Benefit Values | FAMIS Enhancement Request | Send FAMIS Enhancement Request to officially update ACAP and UCI Rates; Send email to budget@tamus.edu to update rates in PBA
Monday, May 1 | PBA | Kelli Holt | Member | Begin running (3x a day) FBAR670, 671 and 665 | FBAR670, 671 and 665 reports available in Laserfiche | Send FAMIS Enhancement Request to officially update ACAP and UCI Rates; Send email to budget@tamus.edu to update rates in PBA
Wednesday, May 10 | PBA | D. Kessner / K. Holt | System Offices | May 10th Snapshot from Workday loaded to PBA; Load costing to sandbox to identify errors early | EDW00212 Prep Cost Allocation Errors | HCM Prep Reports available with May 10th snapshot
Friday, May 5 - Monday, May 29 | SSO | SSO Admin | Member | Update access to users for Position Budgeting Application | SSO SOR | Needed to configure Workday Merit Module
Needed for PBA Access
Wednesday, May 10 | PBA | D. Kessner / K. Holt | System Offices | May 10th Snapshot from Workday loaded to PBA; Load costing to sandbox to identify errors early | EDW00212 Prep Cost Allocation Errors | HCM Prep Reports available with May 10th snapshot
Monday, May 22 - Sunday, Aug 20 | PBA | Kelli Holt | Member | PBA available upon request; Check for Positions on Default Members continuously update PBA to match Workday for: (New Hires, Terminations, Promotions, Transfers) | EDW00179 HCM Prep Template by Adloc Mbr EDW00230 Actions Needed in PBA EDW00214 Differences Comparing PBA to Workday WKDY - Compensation Changes | EDW00214 - another report to identify differences between PBA/WKDY; Compensation Changes - To help identify comp and other changes effective 9/1, which will need to be updated in PBA
Friday, June 16 | FAMIS | J. Eisenrich / K. Holt | Member | Budget and Supplemental items due to System Offices | See SO Budget Office Teams member channel | Narrative, GR Recon, Estimated Beginning Balance, Retention Plant (SO Budget Office - General channel)
Monday, July 17 | FAMIS | J. Eisenrich | Member | Budget marked as "Board Approved"
July - TBD | FAMIS | J. Eisenrich | Member | Due: Programmatic Budget Review Presentations / Board Agenda Items to Board Office
Monday, June 26 - Monday, July 31 (Start and end times are member specific) | PBA / EDW | Kelli Holt | Member | * Update costing allocations in PBA
|  |  |  | Earliest launch for Workday Merit / End of 88th Regular Session | EDW00212 Prep Cost Allocation Errors | Business Objects Report: used to verify PBA entry is correct; provides salary totals by SL-SA
|  |  |  | * Schedule Prep 901's to run or refresh manually | EDW00016 Prep 901 by Source Mbr | Identifies costing allocations that will not load to Workday due to various reasons
Monday, July 10 - Monday, Aug 14 | FAMIS | FAMIS Help | Member | * Optional: Run FAMIS FBAU584/672
| EDW | Kelli Holt | Member | * Optional: Reconcile PBA salaries to 589/599 | HCM Prep (PBA) to FAMIS Budget Salary Comparison | Business Objects Report: Identifies salaries on costing allocations with no submitted budget in FAMIS; Unique to each member; Email Kelli Holt if interested
Friday, Jul 28 | WD | Sri Kamarthi | Member | Request One-Time (OT) Merit EIB's from Sri Kamarthi | OT Merit EIB
August - TBD |  | J. Eisenrich | Member | FY 2024 Programmatic Budget Reviews with Board
Monday, July 31 - Friday, Aug 18 | WD | Sri Kamarthi | Member | Submit completed One-Time (OT) Merit EIB requests to Sri Kamarthi
Monday, Aug 7 |  |  |  | PBA closed to departments (date determined by member)
Tuesday, Aug 8 - Monday, Aug 21 | PBA | Kelli Holt | Member | Central Admin continue manually updating PBA as needed | EDW00212 Prep Cost Allocation Errors EDW00214 Differences Comparing PBA to Workday EDW00230 Actions Needed in PBA | PBA report that identifies costing allocations that will not load to Workday; BO report that identifies differences between PBA and Current Workday
Wednesday, Aug 16 - Thursday, Aug 17 |  | J. Eisenrich | SO | FY 2024 Budget presented to the Board for approval
Monday, Aug 21 | PBA | Kelli Holt | System Offices | PBA Closed to Central Admin
Wednesday, Aug 22 | PBA | D. Kessner / K. Holt | System Offices | Final PBA Snapshot | HCM Prep - Salary Budget | FY 2022 Salary Budget - should match FAMIS "Done" budget
Thursday, Aug 24 | PBA | D. Kessner / K. Holt | System Offices | Costing allocations post to Workday
Friday, Aug 25 | FAMIS | Jarrett Eisenrich | System Offices | Mark FAMIS Budget with a "D"