## Original (hidden)
Option 1 and 2 Timeline, Action Items, Forms and Reports
| Option 1 | Option 2
Date | Action Item | Action Item | Business Objects Reports | Workday Reports | Form
Friday, May 8 | Submit Merit Configuration Worksheet |  |  |  | Merit Configuration Worksheet
| Submit Merit Partner SOR to Sri Kamarthi to add role to new users |  |  |  | Statement of Responsibility
| Update access to users for Position Budgeting Application |  |  |  | SSO Statement of Responsibility
Monday, May 11 | Snapshot from Workday loaded to PBA
Tuesday, May 12 - Friday, August 7 | Continuously update PBA to match Workday for: (New Hires, Terminations, Promotions, Transfers, Org Structure Changes) |  | Actions Needed in PBA | Compensation Changes
Monday, June 1 | Earliest launch for Workday Merit | PBA available per request
Option 2
Monday, June 1 - Monday, August 3 |  | Upload fund blind salary increase .csv file to PBA or enter % increases manually | Report
|  | Schedule Prep 901's to run daily | HCM Prep 901
Update costing allocations in PBA
|  | Correct costing errors posted to Sandbox | Costing Allocation Errors
|  | Optional: Run FBAU584/672 | Board Budget to Current Submitted Budget
|  | Reconcile PBA salaries to 589/599 | Prep to FAMIS Salary Comparison
Monday, August 3 |  | PBA closed to departments
Tuesday, August 4 |  | Workday Merit Launches
Tuesday, August 4 - Friday, August 7 |  | PBA Merit EIB file loaded to Workday Merit
|  | Verify Workday Merit = PBA; correct errors | HCM Prep to Workday Merit Increase Report
Friday, August 7 |  | PBA closed to Central Admin
Monday, August 10 - Monday, August 17 |  | Update Workday Merit as needed
Option 1
Monday, June 1 - Wednesday, July 15 | Merit Planners/Managers complete Workday Merit Entry
Thursday, July 16 | Workday Merit upload to PBA |  | Workday Merit Entry
Friday, July 17 - Friday, August 7 | Update costing allocations in PBA
| Correct costing Errors identified in Sandbox |  | Costing Allocation Errors
| Optional: FBAU584/672 |  | Board Budget vs. Current Submitted Budget
| Run Daily Prep 901's |  | HCM Prep 901's
| Reconcile PBA salaries to 589/599 salaries |  | Prep to FAMIS Salary Comparison
Friday, August 7 | PBA closed to departments
Monday, August 10- Monday, August 17 | PBA Central Admin finalize entry; Correct costing allocation errors |  | Costing Allocation Errors
Monday, August 17 | Workday Merit Finalized
Monday, August 24 | Final PBA Snapshot |  | Salary Budget
Thursday, August 27 | Costing allocations post to Workday
Friday, August 28 | Mark FAMIS Budget with a "D"

## Options 1 & 2
Option 1 and 2 Timeline, Action Items, and Reports
Dates | Option 1 | Option 2 | Resources
| Action Item | Action Item | Forms/Reports/Templates | Purpose:
Friday, May 7 - Monday, May 31 | Submit Merit Configuration Worksheet - Select Option 1 or 2 (3-weeks prior to launch) |  | Merit Configuration Worksheet
| Submit Merit Partner SOR to Sri Kamarthi to add role to new users |  | Merit Partner SOR
| Update access to users for Position Budgeting Application |  | SSO SOR | Needed for PBA Access
Wednesday, May 12 | Snapshot from Workday loaded to PBA
Monday, May 31 - Sunday, August 15 | PBA available upon request; Members continuously update PBA to match Workday for: (New Hires, Terminations, Promotions, Transfers) |  | Actions Needed in PBA EDW00214 - Differences between PBA/Workday WKDY - Compensation Changes | EDW00214 - another report to identify differences between PBA/WKDY; Compensation Changes - To help identify comp and other changes effective 9/1, which will need to be updated in PBA
Monday, May 31 | Earliest launch for Workday Merit
Option 1
Monday, May 31 - Wednesday, July 14 | Merit Planners/Managers complete Workday Merit Entry and Submit
Thursday, July 15 - Monday, August 9 Start and end dates are member specific | * Workday Merit upload to PBA-multiple uploads via .csv are possible |  | EDW00217 HCM Workday Merit Entry Upload to PBA; HCM Prep (PBA)<>Workday Merit Entry (in dev) | Business Objects report that includes Position ID, UIN, % Increase for Merit; % Increase for Promotion and % Increase for Other Adjustments. File will be used to populate PBA, if there is a match of Position ID/UIN combination in both applications.
* Update costing allocations in PBA
| * Correct costing Errors identified in Sandbox |  | TBD - Costing Allocation Errors from Sandbox | Identifies costing allocations that will not load to Workday due to various reasons
* Optional: Run FAMIS FBAU584/672
| * Run Prep 901 |  | EDW00016 - HCM Prep 901 by Source Mbr | Business Objects Report: To verify PBA entry is correct; provides salary totals by SL-SA
| * Optional: Reconcile PBA salaries to 589/599 salaries |  | HCM Prep (PBA) to FAMIS Salary Comparison | Business Objects Report: Identifies salaries on costing allocations with no submitted budget in FAMIS; Unique to each member
Monday, August 9 | PBA closed to departments (date determined by member)
Option 2
Tuesday, May 12 - Monday, May 31 |  | Email Kelli Holt to request the Departmental Salary Increase Template - supply Workstation when requesting excel file
Wednesday, June 30 - Monday, August 16 Start and end times are member specific |  | At member discretion, upload salary increase template .csv file to PBA or enter % increases manually in PBA
* Update costing allocations in PBA
|  | * Schedule Prep 901's to run or refresh manually | EDW00016 - HCM Prep 901 by Source Mbr | Business Objects Report: used to verify PBA entry is correct; provides salary totals by SL-SA
|  | * Correct costing errors posted to Sandbox | EDW00212-HCM Prep Costing Allocation Errors | Identifies costing allocations that will not load to Workday due to various reasons
Thursday, July 16 - Monday, August 16 |  | * Optional: Run FAMIS FBAU584/672
|  | * Optional: Reconcile PBA salaries to 589/599 | HCM Prep (PBA) to FAMIS Budget Salary Comparison | Business Objects Report: Identifies salaries on costing allocations with no submitted budget in FAMIS; Unique to each member; Email Kelli Holt if interested
Monday, August 2 - Tuesday, August 3 |  | Test PBA EIB load to WKDY sandbox per Member request to identify errors; address errors | Request EIB to load costing allocations in WD Sandbox - do this on a Monday; EIB Posting Errors in Sandbox | Exact process TBD
Wednesday, August 4 - Monday, August 16 |  | * Launch Workday Merit and Load EIB (1X/member); Date of EIB upload = member's merit launch date * Run exceptions report to identify differences between PBA and Workday Merit * Correct differences until PBA and WKDY merit closes | HCM Prep <> Workday Merit Report (in dev) | Business Objects report that compares the merit entry in PBA to what was loaded via EIB from PBA to Workday Merit
Monday, August 9 |  | PBA closed to departments (date determined by member)
Combined for both Options
Tuesday, August 10 - Sunday, August 15 | Central Admin continue manually updating Workday Merit and PBA as needed |  | Workday-Merit Awards on Hold Audit; Costing Error Reports; EDW00214 - Differences between PBA/Workday | Workday report that identifies merits on hold because of an in-progress Business Process; PBA report that identifies costing allocations that will not load to Workday; BO report that identifies differences between PBA and Current Workday
Monday, August 16 | PBA Closed to Central Admin/Workday Merit Finalized Systemwide
Monday, August 23 | Final PBA Snapshot |  | HCM Prep - Salary Budget | FY 2021 Salary Budget - should match FAMIS "Done" budget
Thursday, August 26 | Costing allocations post to Workday
Friday, August 27 | Mark FAMIS Budget with a "D"

## Option 3
Option 3 Timeline, Action Items, and Reports
Dates | Option 3 | Resources
| Action Item | Forms/Reports/Templates: | Purpose:
Friday, May 7 | Update access to users for Position Budgeting Application | SSO SOR | Needed for PBA Access
Wednesday, May 12 | Snapshot from Workday loaded to PBA
Monday, May 31 - Sunday, August 15 | PBA available upon request; Members continuously update PBA to match Workday for: (New Hires, Terminations, Promotions, Transfers) | EDW00214 - Differences between PBA/Workday WKDY - Compensation Changes | EDW00214 - another report to identify differences between PBA/WKDY; Compensation Changes - To help identify comp and other changes effective 9/1, which will need to be updated in PBA
* Update costing allocations in PBA
| * Correct costing Errors identified in Sandbox | TBD - Costing Allocation Errors from Sandbox | Identifies costing allocations that will not load to Workday due to various reasons
* Optional: Run FAMIS FBAU584/672
| * Run Prep 901 | EDW00016 - HCM Prep 901 by Source Mbr | Business Objects Report: To verify PBA entry is correct; provides salary totals by SL-SA
| * Optional: Reconcile PBA salaries to 589/599 salaries | HCM Prep (PBA) to FAMIS Salary Comparison | Business Objects Report: Identifies salaries on costing allocations with no submitted budget in FAMIS; Unique to each member; Email Kelli Holt if interested
Monday, August 16 | PBA Closed to Central Admin/Workday Merit Finalized Systemwide
Monday, August 23 | Final PBA Snapshot | HCM Prep - Salary Budget | FY 2021 Salary Budget - should match FAMIS "Done" budget
Thursday, August 26 | Costing allocations post to Workday
Friday, August 27 | Mark FAMIS Budget with a "D"