## Risk Assessment
Risk Assessment Exercise
Requisition No.:
Project Name:
Instructions: For all projects, rate project factors 1-10. For Information Technology projects only, add
project factors 11-13. Enter the appropriate number for the project factor range that applies to the project.
RANGE | FACTORS FOR COMMODITY, SERVICES AND IT PROJECTS | SCORE
1. Total Contract Price: What is the estimated price for the anticipated base period of the contract?
0 | < $100,00
1 | Low Contract Price -Between $100,000 - $250,000
2 | Moderate Contract Price - Between $250 - $1 Million
3 | Important Contract Price - Between $1 Million and $5 Million
4 | High Contract Price - > $5 Million
Agency comment:
2. Total Contract Duration: What is the anticipated overall potential contract period (base year plus
option years)?
0 | < One year
1 | One to two years
2 | Two to five years
4 | Greater than five years
Agency comment:
3. User Involvement: How many end users do you anticipate for this contract:
0 | No agencies
1 | One agency
2 | Multiple agencies
4 | Statewide or outside groups
Agency comment:
4. Criticality of Deliverables: Which delivery requirements best describes your project?
0 | No urgency in deliverable timing
1 | Deliverable timing is important, but not critical
3 | Deliverable timing is critical
4 | Deliverable timing is critical and must take priority over all other projects.
Agency comment:
5. Contract Failure Impact: Which of the following best describes the users impacted by a contract
failure?
0 | Low risk optional use contract with no legal mandate
1 | Failure will impact internal department operations only
3 | Failure will impact internal and external users
4 | Failure would have a statewide impact, violate state and or federal mandates or result in the loss
of substantial funds.
Agency comment:
6. Locations Impacted: Which of the following best describes the locations affected by this contract?
0 | Contract will be implemented in or hosted from a single location
2 | Contract will be implemented across multiple agency sites
4 | Contract will be implemented statewide
Agency comment:
7. Availability of Resources for Contract Management: Which of the following best describe the
resource requirements of this project?
0 | Not applicable
1 | Adequate staffing is readily available to manage and support the contract, including SME's
3 | Temporary staffing is needed to supplement end-user staff to manage and/or support the contract.
4 | Full-time consultants or temporary staffing is needed to manage and/or support the contract.
Agency comment:
8. Complexity of Project: Which best describes the project's complexity?
0 | Simple commodity or service with clear specifications
2 | Complex requirements involving internal expertise
4 | Very complex requirements involving external technical experts/evaluators/legal review
Agency comment:
9. Business Process Impact: Level of impact to end user's business process?
0 | Not applicable
1 | Business processes from a single business unit within an agency will be impacted
2 | Business processes from an entire agency will be impacted
3 | Business processes from multiple agencies will be impacted
4 | Business process change is statewide
Agency comment:
10. End Users' Training Needs: Indicate the appropriate training requirements for this project?
0 | No training required
1 | End-user only training required
3 | Systems and end-users require training and support that be conducted by in-house trainers
4 | Systems and end-users requires training and support by the vendor or an outside trainer
Agency comment:
RISK ASSESSMENT SCORE FOR FACTORS 1-10
RANGE | COMPLETE FACTORS 11-13 FOR INFORMATION TECHNOLOGY PROJECTS ONLY
11. Software Technology Customization: What level of customization is required for this solution?
0 | All requirements can be satisfied with mature or Commercial Off-The-Shelf (COTS) products
2 | The requirement may be partially customized and partially COTS
4 | Fully customized solution
Agency comment:
12. Impact on Existing Application or Infrastructure: Which of the following best describes
the impact on existing infrastructure for this project?
0 | Maintenance
2 | Product is an enhancement to the existing application or infrastructure
3 | Product is a replacement of the existing application or infrastructure
4 | Product is new and impact other existing applications or infrastructure
Agency comment:
13. Interface Connectivity: Which of the following best describes the interface connectivity of the
proposed system?
0 | Not applicable or existing without new interfaces
2 | The new system will interface with 1-4 existing applications
4 | The new system will interface with 5 or more applications
Agency comment:
IT RISK ASSESSMENT SCORE FOR FACTORS 11-13
TOTAL RISK ASSESSMENT SCORE
Risk Assessment Report Score: Commodities and Services
Score | 0-10 = Low Risk
Score | 11-20 = Moderate Risk
Score | 21-30 = Important Risk
Score | 31-40 = High Risk
Risk Assessment Report Score: Information Technology
Score | 0-13 = Low Risk
Score | 14-26 = Moderate Risk
Score | 27-39 = Important Risk
Score | 40-52 = High Risk

## Risk Mitigation
Instructions: Risk mitigation is recommended for all projects with an Important (3) or High (4) risk classification. Transfer the project factor scores from the Risk Assessment Tool to the corresponding row on the worksheet. Individual project factors with a score of 3 and above should be reviewed for possible risk mitigation strategies. Any strategies should be incorporated into the Terms and Conditions and RFP language.
RISK | RISK FACTOR | Mitigation, Containment and Contingency Strategies | Responsible | Target
SCORE |  |  | Party | Date
1. Total Contract Price: The higher the dollar value of the contract, the greater potential cost to the agency in the event that the vendor is unable to perform their contractually obligated responsibilities.
2. Contract Duration: The greater the length of the contract (base plus optional years), the greater likelihood that changes may occur in key variables such as: personnel, customer's environment, general business climate, etc. Such changes can affect the outcome of the contract.
3. User Involvement: The greater the number of agencies involved and/or impacted by the implementation of the contract, the greater the complexity of the initiative in terms of coordination.
4. Criticality of Deliverables: The degree to which the procurement process is expedited must be assessed to determine associated risks. Projects requiring urgent deliverables may require greater management.
5. Contract Failure Impact: The impact of a failure to fulfill the contract varies depending on the scope of the parties affected.
6. Locations Impacted: The more locations impacted by the contract, the greater the complexity of the initiative and thus the higher the risk associated with the contract.
7. Availability of Resources for Contract Management: All contracts must be closely managed. It is important that the agency/end-user provide sufficient resources to manage and support the performance of the contract.
8. Complexity of Project: The development of the SOW and RFP requirements is critical to establish a contract that accurately projects the needs of the agency relative to the completion of the project. Incomplete or complex requirements in the RFP increases the risk associated with the contract.
9. Business Process Impact: Refers to the extent of which existing business processes will be impacted with contract implementation or failure to implement the contract.
10. End User Training Needs: Refers to the risks associated with not having the requisite skills to adapt to new policies, procedures and/or technology.
Risk Factors 11-13 are for Information Technology Projects
11. Software Technology Customization: Products that have been widely used for more than a year are considered mature. These types of products are typically reliable and pose little risk. However, pre-released or newly released products using "leading-edge" technology, pose greater risks. Highly customized products also pose greater risks than standard or configurable products (e.g. COTS packages)
12. Impact on Existing Application or Infrastructure: The greater the impact the implementation of the contract will have on the existing application or environment, the greater the potential risk of the project.
13. Interface Connectivity: The higher the number of existing applications a new system must connect to, the higher risk for contract implementation.