## Project Complexity
Complexity Assessment | [6 empty] | Task
Level 1
Website Redesign | [6 empty] | Level 2
TAC 216 Companion Guide Version: |  | 2018 |  |  |  |  | Level 3
Document Version: |  | 1 |  |  |  |  | Level 4
Date Completed: |  | (date)
Completed by: |  | (name)
Project managers should thoroughly evaluate a project's potential risks and understand the project's complexity before starting it. This evaluation also helps identify issues before they can affect the project's successful completion. Use this Complexity Assessment to help you systematically evaluate the risks and complexities of this project.
Is this a Major Information Resources Project (MIRP)? (As defined by System Internal Audit ) |  |  |  | Yes / No | Not A MIRP | Notes
Takes one year or longer to reach operational status |  |  |  | NO
Has development, implementation or procurement costs of $1 million or more |  |  |  | NO
Involves more than one A&M System member |  |  |  | NO
Significantly alters work methods of core administrative and business processes and supports financial, personnel or strategic decision-making |  |  |  | NO
For each criteria below, assign a weight, describe how the criteria applies to the project and indicate how much complexity the criteria adds to the project.
Complexity Criteria | Assign Weight between 0 & 1 | How does the criteria apply to this project? | NA | Low High | Criteria Score | Notes
|  | Select an Option from Drop Down Menu if Applicable | 0 | 1 2 3 4 5
Sponsor | 0.5 | Two | 3 |  | 1.5
Project Objectives | 0.5 | Some ambiguity | 3 |  | 1.5
Mandates (TAC, SAP, System) | 0.7 | No | 1 |  | 0.7
Internal Work Processes | 0.4 | Unfamiliar | 5 |  | 2
Technical Requirements | 0.5 | Familiar | 1 |  | 0.5
Team Location | 0.5 | Many | 5 |  | 2.5
End User Impact | 0.8 | High | 5 |  | 4
Deadline | 0.8 | Flexible Schedule, no deadline | 1 |  | 0.8
Initial Project Effort Estimate (+/-75%) | 0.7 | 1 month - 6 months | 3 |  | 2.1
Initial Project Cost Estimate (+/-75%) | 1 | < $50,000 | 1 |  | 1
Team Expertise | 0.8 | Somewhat experienced | 3 |  | 2.4
Team Size | 0.8 | 8 - 20 team members | 2 |  | 1.6
Team Availability | 0.5 | Very limited | 5 |  | 2.5
Stakeholder Involvement | 0.6 | 20-80 people | 5 |  | 3
External Dependencies | 0.8 | None | 0 |  | 0
Totals | 9.9 |  |  |  | 26.1
Project Complexity Score: |  |  |  | 2.6364
Recommended Project Level: |  |  |  | 2
Assigned Project Level: | (Task, Level 1, Level 2, Level 3 or Level 4) |  |  | Level 2
This project is intended to re-design an existing website. Scope included:
* It was "sponsored" by two individuals
* Scope was mostly understood, with some confusion/disagreement amongst stakeholders
* There were no mandates for completion
* The work processes to develop and modify utilized a new methodology, and so unfamiliar was selected
* The technical processes/requirements were clear
* The team was geographically separated
* There was a high end user impact
* There was no deadline
* The original estimates were approximately 6 months, and less than $50,000
* The teams were technically proficient but were using new methods
* The team was expected to not exceed 20 individuals
* The team availability was sparse, with multiple conflicts abounding
* Stakeholders interested in the project exceed 80
* There were no external dependences
Note on B19: Assign a Weight between 0.0 and 1.0 to each criteria to indicate which are most important for this project (0.5 - 1.0) and which are less important for this project (0.0 - 0.5).
Note on E19: Using your answer in Column C, enter 0 - 5 to indicate how much complexity is added to this project.
Note on A21: A senior manager with a vested interest in the outcome of the project. If the project is a part of a larger effort (program), then the project sponsor can be the program manager for the entire effort.
Note on A22: Project scope and objectives should be clearly understood and describe what the project is trying to achieve. Is the scope of this project clearly defined? Was a clear definition of the objectives (deliverables) received for accomplishing this project?
Note on A23: Examples include: TAC, SAP, Audit Finding, A&M System Policy
Note on A24: How well established are the work processes and standards that the project will be using? Are processes in place for communicating with stakeholders, receiving approval and feedback?
Note on A25: Are the project's technical requirements familiar to the group? In the past, has the group developed or delivered similar requirements?
Note on A26: What is the general location of the team? Are team members located in the same building, division, or organization?
Note on A27: What is the impact to the end user? Would the project's failure cause a critical situation?
Note on A28: Has a firm deadline to deliver the project been established? Will the deadline allow us to complete the project timely, or is it too restrictive?
Note on A29: Based on the initial estimate, how many ‘working hours’ will be required to complete the project? Estimates in the early-stages typically fall in the +/- 75% range, but can be more precise if additional data and subject matter expertise is available.
Note on A30: Based on the initial estimate, how much will it cost to complete the project? Estimates in the early-stages typically fall in the +/- 75% range, but can be more precise if additional data and subject matter expertise is available.
Note on A31: Is the team experienced at delivering similar work?
Note on A32: How large is the project team? What is the number of people needed to work on this project?
Note on A33: Are team members available? Are there conflicting priorities?
Note on A34: Outside the project team, how many people need to be kept up to date on the project progress? How complex are the communication needs going to be?
Note on A35: Does project success depend upon vendors, other departments, or other projects?

## Values (hidden)
Sponsor |  | MIRP
< Select an Option > |  | < Select an Option >
One | 1 | YES
Two | 3 | NO
None or Many | 5
Project Level
Objectives
< Select an Option >
Clear and reasonable | 1 | 1 | 1 | 1.9
Some ambiguity | 3 | 2 | 2 | 2.9
Vague or unreasonable | 5 | 3 | 3 | 3.9
|  | 4 | 4
Mandates
< Select an Option >
No | 1
Yes | 5
Work_Process
< Select an Option >
Familiar | 1
Somewhat familiar | 3
Unfamiliar | 5
Technical
< Select an Option >
Familiar | 1
Somewhat familiar | 3
Unfamiliar | 5
Location
< Select an Option >
One | 1
Two | 3
Many | 5
Impact
< Select an Option >
Low | 1
Moderate | 3
High | 5
Deadline
< Select an Option >
Flexible Schedule, no deadline | 1
Moderate schedule or internal deadline | 3
Tight schedule or mandated deadline | 5
Effort
< Select an Option >
< 1 week | 1
1 week - 1 month | 2
1 month - 6 months | 4
> 6 months | 5
Cost
< Select an Option >
< $50,000 | 1
$50,000 - $249,999 | 2
$250,000 - $499,999 | 3
$500,000 - $999,999 | 4
> $1,000,000 | 5
Expertise
< Select an Option >
Experienced | 1
Somewhat experienced | 3
Inexperienced | 5
Team_Size
< Select an Option >
< 8 team members | 1
8 - 20 team members | 2
20-40 team members | 4
>40 members | 5
Availability
< Select an Option >
Available | 1
Partially available | 3
Very limited | 5
Stakeholders
< Select an Option >
< 2 people | 1
3-10 people | 2
10-20 people | 4
20-80 people | 5
Dependencies
< Select an Option >
None | 0
One, Minimally Dependent | 1
Several or Moderately Dependent | 3
Many or Highly Dependent | 5