## Combined Checklist
[5 empty] | Project: | <Project>
TAC 216 Checklist of Activities and Tasks that can be added to a project |  |  |  |  | Level: | 0
[5 empty] | R | A Required activity or task
[5 empty] | E | An Encouraged activity or task
Initiating Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Related Templates
Develop Business Case |  |  | X | X
Project Overview
Business Need |  |  | E | R |  |  | -Business Case
Business Goals/Objectives |  |  | E | R |  |  | -Business Case
Recommendation |  |  | E | R |  |  | -Business Case
Justification and Impact |  |  | E | R |  |  | -Business Case
Customer |  |  | E | R |  |  | -Business Case
Project Manager Involvement |  |  | E | R |  |  | -Business Case
Projected Project Budget and Funding Source |  |  | E | R |  |  | -Business Case
Assumptions |  |  | E | R |  |  | -Business Case
Limitations/Constraints |  |  | E | R |  |  | -Business Case
Risks |  |  | E | R |  |  | -Business Case
Project Evaluation
Strategic Alignment |  |  | E | R |  |  | -Business Case
Business Value |  |  | E | R |  |  | -Business Case
Institution/Agency Priority |  |  | E | R |  |  | -Business Case
Develop Charter
Project Information
Project Name | R | R | R | R |  |  | -Level 1 Project -Project Charter
Performing Organization | R | R | R | R |  |  | -Level 1 Project -Project Charter
Project Overview
What are you trying to achieve? | R | R | R | R |  |  | -Level 1 Project -Project Charter
Why is this important? How does it align to business goals and objectives? | R | R | R | R |  |  | -Level 1 Project -Project Charter
How will success be measured? Financial/Quantitative - are you retiring a piece of hardware, software, recovering a license cost? Business Impact - are you expanding a workflow, bringing new functionality to end users, including more end users in a workflow? | R | R | R | R |  |  | -Level 1 Project -Project Charter
Scope
What are you going to do? | R | R | R | R |  |  | -Level 1 Project (only defined through milestones) -Project Charter
What is explicitly not going to be included? | R | R | R | R |  |  | -Level 1 Project (only defined through milestones) -Project Charter
Stakeholders
Project Sponsor(s) | R | R | R | R |  |  | -Level 1 Project -Project Charter
Project Manager | R | R | R | R |  |  | -Level 1 Project -Project Charter
Other key stakeholders | R | R | R | R |  |  | -Level 1 Project -Project Charter
Schedule, budget, and resources
Develop a rough schedule | R | R | R | R |  |  | -Level 1 Project -Project Charter
Develop a rough budget |  | R | R | R |  |  | -Project Charter
Define funding and oversight authority |  |  | R | R |  |  | -Project Charter
Identify key resources, roles, and responsibilities | R | R | R | R |  |  | -Level 1 Project -Project Charter
Risk and quality considerations
What can go wrong? | R | R | R | R |  |  | -Level 1 Project -Project Charter
Does the project involve confidential information? | R | R | R | R |  |  | - Complexity Assessment '-Level 1 Project -Project Charter
Is the project subject to Internal Audit oversight? |  |  | R | R |  |  | -Project Charter
Assumptions and Constraints
Describe any assumptions about the events or circumstances you are expecting to occur during the project | R | R | R | R |  |  | -Level 1 Project -Project Charter
Describe limitations or restrictions that may impact execution of the project | R | R | R | R |  |  | -Level 1 Project -Project Charter
Prioritize the triple constraints (scope, time, cost) |  | R | R | R |  |  | -Project Charter
Who will support/operate the result when the project ends? |  | R | R | R |  |  | -Project Charter
Approve Charter for planning | R | R | R | R
Identify stakeholders | R | R | R | R
Create document repository (See Appendix D - Project Document Management) and collaboration environment | R | R | R | R
Planning Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Related Templates
Prepare a baseline Project Plan Address the following topics in the appropriate detail
Scope
Develop a statement of scope | R | R | R | R |  |  | -Level 1 Project (through Deliverables) -Project Charter -Project Plan
Develop a list of requirements |  | E | E | R |  |  | -Project Plan
Develop a list of deliverables | E | E | E | E |  |  | -Level 1 Project -Project Charter -Project Plan
Develop a work breakdown structure * Include Change Management activities and tasks as appropriate (See Appendix F - Organizational Change Management) |  | E | R | R |  |  | -Project Plan
Schedule
Update the schedule | R | R | R | R |  |  | -Level 1 Project -Project Plan
Provide the level of uncertainty for estimates |  | E | R | R |  |  | -Project Plan
Document work assignments |  | E | R | R |  |  | -Project Plan
Budget and Oversight
Update the budget |  | E | R | R |  |  | -Project Plan
Provide the level of uncertainty for estimates |  | E | R | R |  |  | -Project Plan
Who will approve the budget? |  |  | E | R |  |  | -Project Plan
Develop the procurement plan |  | E | R | R |  |  | -Project Plan
Resources, roles, and responsibilities
Develop a RACI (Responsible, Accountable, Consulted, and Informed) chart for project milestones | E | R | R | R |  |  | -Project Plan
Risks
Identify and analyze risks | E | E | R | R |  |  | -Project Plan
Plan for risk prevention and response | E | E | R | R |  |  | -Project Plan
Formalize the risk register | R | R | R | R |  |  | -Project Plan
Quality
Identify applicable quality standards | E | E | R | R |  |  | -Project Plan
Define quality assurance and control processes |  |  | E | R |  |  | -Project Plan
Communication
Develop project communication plan - identify who needs to know what and when and how information will be disseminated | E | E | R | R |  |  | -Project Plan
Stakeholder Register
Analyze current and desired level of engagement for key stakeholders |  | E | R | R |  |  | -Project Plan
Analyze impacts to stakeholders |  |  | E | R |  |  | -Project Plan
Assumptions and Constraints
Update assumptions and constraints | R | R | R | R |  |  | -Level 1 Project -Project Plan
Change Control
Define how changes to scope, schedule and budget will be requested | R | R | R | R |  |  | -Project Plan
Identify who will receive requests and make decisions | R | R | R | R |  |  | -Project Plan
Plan frequency of change control board or project steering committee meetings |  |  | E | R |  |  | -Project Plan
Deployment, Stabilization and Transition to Operations
Define the project deployment approach and processes | R | R | R | R |  |  | -Project Plan
Plan how the result will be transitioned to operational status |  | E | R | R |  |  | -Project Plan
Describe project support requirements - who will be responsible for meeting these requirements? | R | R | R | R |  |  | -Project Plan
Develop Executing, Monitoring & Controlling templates Change Log Status Report Issues Log | R | R | R | R |  |  | -Project Change Request -Lessons Learned Report
Approve Plan for Executing | R | R | R | R
Executing Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Related Templates
Execute, Monitor, and Control the Project
Build and train the project team | E | E | R | R |  |  | -TAC 216 Companion Guide
Ensure key stakeholders are familiar with the Project Plan: -Project goals and objectives -Project budget and schedule -Project team roles and responsibilities, and collaboration methods/tools -Critical success factors and deliverables acceptance criteria -Risk and issue management processes -Project communication strategy -Change control processes | R | R | R | R |  |  | -Level 1 Project -Executing, Monitoring & Controlling -Project Change Request -Project Log -Risk Register -Communication Plan -Project Portfolio
Critical success factors and deliverables acceptance criteria | R | R | R | R |  |  | -Level 1 Project -Executing, Monitoring & Controlling -Project Change Request
Risk and issue management processes | R | R | R | R |  |  | -Level 1 Project -Project Change Request -Project Log -Risk Register
Project communication strategy | E | E | R | R |  |  | -Communication Plan
Change control processes | E | E | E | R |  |  | -Project Change Request
Perform project work including quality assurance and procurement activities | R | R | R | R |  |  | -Level 1 Project -Executing, Monitoring & Controlling -Project Change Request -Project Log -Risk Register -Communication Plan -Project Portfolio
Track progress of actual performance against projected performance and analyze reasons for any variations | R | R | R | R |  |  | -Level 1 Project -Executing, Monitoring & Controlling -Project Change Request -Project Log -Risk Register
Manage project communications and stakeholder engagement | E | E | R | R |  |  | -Level 1 Project -Executing, Monitoring & Controlling -Project Change Request -Project Log -Communication Plan
Capture and communicate requested and approved changes | E | E | E | R |  |  | -Project Change Request -Project Log
Maintain the Project Log: -Review and update the Issues Log -Review and update the Risk Register -Review and update Action Items -Update the Change Log | R | R | R | R |  |  | -Executing, Monitoring & Controlling -Project Change Request -Project Log -Risk Register
Make necessary updates to the Project Plan | R | R | R | R |  |  | -Level 1 Project -Executing, Monitoring & Controlling -Project Change Request
For complex deployments, develop and execute a deployment plan that also addresses communication |  | E | R | R |  |  | -Executing, Monitoring & Controlling -Communication Plan
Obtain signoff on project deliverables | R | R | R | R |  |  | -Executing, Monitoring & Controlling -Project Change Request
Develop Closing templates Lessons Learned Report Post Project Survey | R | R | R | R |  |  | -Post Project Survey -Lessons Learned Report
Closing Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Related Templates
Obtain final acceptance of project completion | R | R | R | R
Close out the project
Deployment and transition to operations
Notify users | R | R | R | R |  |  | -Communication Plan
Develop end-user and operational documentation | R | R | R | R
Transfer knowledge to operational staff and service desk | R | R | R | R
Update information resources management system/configuration management database | E | E | R | R
Update Service Catalog/IT Services list and business processes | R | R | R | R
Establish product/service governance, if applicable | E |  | R | R
Release new products/services | R | R | R | R
Stabilization
Identify and address any open issues on the project | R | R | R | R |  |  | -Project Log
Finalize project backing | E | R | R | R |  |  | -Communication Plan
Close out procurement relationship
Finalize any open claims | R | R | R | R
Update records to reflect final results | R | R | R | R
Evaluate and document vendor performance | R | R | R | R
Conduct lessons learned for continuous improvement | [6 empty] | -Post Project Survey -Lessons Learned Report
Complete Compliance Validation Check list | R | R | R | R |  |  | -Level 1 Project -Project Closure
Project management processes | E | R | R | R
Change management processes | E | R | R | R |  |  | -Project Plan -Project Log
Product/service development processes | E | R | R | R |  |  | -Project Plan
Archive project documents (See AppendiR D - Project Document Management) | R | R | R | R

## Initiating
[5 empty] | Project: | <Project>
TAC 216 Checklist of Activities and Tasks that can be added to a project |  |  |  |  | Level: | 0
[5 empty] | R | A Required activity or task
[5 empty] | E | An Encouraged activity or task
Initiating Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Related Templates
Develop Business Case |  |  | X | X
Project Overview
Business Need |  |  | E | R |  |  | -Business Case
Business Goals/Objectives |  |  | E | R |  |  | -Business Case
Recommendation |  |  | E | R |  |  | -Business Case
Justification and Impact |  |  | E | R |  |  | -Business Case
Customer |  |  | E | R |  |  | -Business Case
Project Manager Involvement |  |  | E | R |  |  | -Business Case
Projected Project Budget and Funding Source |  |  | E | R |  |  | -Business Case
Assumptions |  |  | E | R |  |  | -Business Case
Limitations/Constraints |  |  | E | R |  |  | -Business Case
Risks |  |  | E | R |  |  | -Business Case
Project Evaluation
Strategic Alignment |  |  | E | R |  |  | -Business Case
Business Value |  |  | E | R |  |  | -Business Case
Institution/Agency Priority |  |  | E | R |  |  | -Business Case
Develop Charter
Project Information
Project Name | R | R | R | R |  |  | -Level 1 Project -Project Charter
Performing Organization | R | R | R | R |  |  | -Level 1 Project -Project Charter
Project Overview
What are you trying to achieve? | R | R | R | R |  |  | -Level 1 Project -Project Charter
Why is this important? How does it align to business goals and objectives? | R | R | R | R |  |  | -Level 1 Project -Project Charter
How will success be measured? Financial/Quantitative - are you retiring a piece of hardware, software, recovering a license cost? Business Impact - are you expanding a workflow, bringing new functionality to end users, including more end users in a workflow? | R | R | R | R |  |  | -Level 1 Project -Project Charter
Scope
What are you going to do? | R | R | R | R |  |  | -Level 1 Project (only defined through milestones) -Project Charter
What is explicitly not going to be included? | R | R | R | R |  |  | -Level 1 Project (only defined through milestones) -Project Charter
Stakeholders
Project Sponsor(s) | R | R | R | R |  |  | -Level 1 Project -Project Charter
Project Manager | R | R | R | R |  |  | -Level 1 Project -Project Charter
Other key stakeholders | R | R | R | R |  |  | -Level 1 Project -Project Charter
Schedule, budget, and resources
Develop a rough schedule | R | R | R | R |  |  | -Level 1 Project -Project Charter
Develop a rough budget |  | R | R | R |  |  | -Project Charter
Define funding and oversight authority |  |  | R | R |  |  | -Project Charter
Identify key resources, roles, and responsibilities | R | R | R | R |  |  | -Level 1 Project -Project Charter
Risk and quality considerations
What can go wrong? | R | R | R | R |  |  | -Level 1 Project -Project Charter
Does the project involve confidential information? | R | R | R | R |  |  | - Complexity Assessment '-Level 1 Project -Project Charter
Is the project subject to Internal Audit oversight? |  |  | R | R |  |  | -Project Charter
Assumptions and Constraints
Describe any assumptions about the events or circumstances you are expecting to occur during the project | R | R | R | R |  |  | -Level 1 Project -Project Charter
Describe limitations or restrictions that may impact execution of the project | R | R | R | R |  |  | -Level 1 Project -Project Charter
Prioritize the triple constraints (scope, time, cost) |  | R | R | R |  |  | -Project Charter
Who will support/operate the result when the project ends? |  | R | R | R |  |  | -Project Charter
Approve Charter for planning | R | R | R | R
Identify stakeholders | R | R | R | R
Create document repository (See Appendix D - Project Document Management) and collaboration environment | R | R | R | R

## Planning
[5 empty] | Project: | <Project>
TAC 216 Checklist of Activities and Tasks that can be added to a project |  |  |  |  | Level: | 0
[5 empty] | R | A Required activity or task
[5 empty] | E | An Encouraged activity or task
Planning Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Related Templates
Prepare a baseline Project Plan Address the following topics in the appropriate detail
Scope
Develop a statement of scope | R | R | R | R |  |  | -Level 1 Project (through Deliverables) -Project Charter -Project Plan
Develop a list of requirements |  | E | E | R |  |  | -Project Plan
Develop a list of deliverables | E | E | E | E |  |  | -Level 1 Project -Project Charter -Project Plan
Develop a work breakdown structure * Include Change Management activities and tasks as appropriate (See Appendix F - Organizational Change Management) |  | E | R | R |  |  | -Project Plan
Schedule
Update the schedule | R | R | R | R |  |  | -Level 1 Project -Project Plan
Provide the level of uncertainty for estimates |  | E | R | R |  |  | -Project Plan
Document work assignments |  | E | R | R |  |  | -Project Plan
Budget and Oversight
Update the budget |  | E | R | R |  |  | -Project Plan
Provide the level of uncertainty for estimates |  | E | R | R |  |  | -Project Plan
Who will approve the budget? |  |  | E | R |  |  | -Project Plan
Develop the procurement plan |  | E | R | R |  |  | -Project Plan
Resources, roles, and responsibilities
Develop a RACI (Responsible, Accountable, Consulted, and Informed) chart for project milestones | E | R | R | R |  |  | -Project Plan
Risks
Identify and analyze risks | E | E | R | R |  |  | -Project Plan
Plan for risk prevention and response | E | E | R | R |  |  | -Project Plan
Formalize the risk register | R | R | R | R |  |  | -Project Plan
Quality
Identify applicable quality standards | E | E | R | R |  |  | -Project Plan
Define quality assurance and control processes |  |  | E | R |  |  | -Project Plan
Communication
Develop project communication plan - identify who needs to know what and when and how information will be disseminated | E | E | R | R |  |  | -Project Plan
Stakeholder Register
Analyze current and desired level of engagement for key stakeholders |  | E | R | R |  |  | -Project Plan
Analyze impacts to stakeholders |  |  | E | R |  |  | -Project Plan
Assumptions and Constraints
Update assumptions and constraints | R | R | R | R |  |  | -Level 1 Project -Project Plan
Change Control
Define how changes to scope, schedule and budget will be requested | R | R | R | R |  |  | -Project Plan
Identify who will receive requests and make decisions | R | R | R | R |  |  | -Project Plan
Plan frequency of change control board or project steering committee meetings |  |  | E | R |  |  | -Project Plan
Deployment, Stabilization and Transition to Operations
Define the project deployment approach and processes | R | R | R | R |  |  | -Project Plan
Plan how the result will be transitioned to operational status |  | E | R | R |  |  | -Project Plan
Describe project support requirements - who will be responsible for meeting these requirements? | R | R | R | R |  |  | -Project Plan
Develop Executing, Monitoring & Controlling templates Change Log Status Report Issues Log | R | R | R | R |  |  | -Project Change Request -Lessons Learned Report
Approve Plan for Executing | R | R | R | R

## Executing
[5 empty] | Project: | <Project>
TAC 216 Checklist of Activities and Tasks that can be added to a project |  |  |  |  | Level: | 0
[5 empty] | R | A Required activity or task
[5 empty] | E | An Encouraged activity or task
Executing Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Related Templates
Execute, Monitor, and Control the Project
Build and train the project team | E | E | R | R |  |  | -TAC 216 Companion Guide
Ensure key stakeholders are familiar with the Project Plan: -Project goals and objectives -Project budget and schedule -Project team roles and responsibilities, and collaboration methods/tools -Critical success factors and deliverables acceptance criteria -Risk and issue management processes -Project communication strategy -Change control processes | R | R | R | R |  |  | -Level 1 Project -Executing, Monitoring & Controlling -Project Change Request -Project Log -Risk Register -Communication Plan -Project Portfolio
Critical success factors and deliverables acceptance criteria | R | R | R | R |  |  | -Level 1 Project -Executing, Monitoring & Controlling -Project Change Request
Risk and issue management processes | R | R | R | R |  |  | -Level 1 Project -Project Change Request -Project Log -Risk Register
Project communication strategy | E | E | R | R |  |  | -Communication Plan
Change control processes | E | E | E | R |  |  | -Project Change Request
Perform project work including quality assurance and procurement activities | R | R | R | R |  |  | -Level 1 Project -Executing, Monitoring & Controlling -Project Change Request -Project Log -Risk Register -Communication Plan -Project Portfolio
Track progress of actual performance against projected performance and analyze reasons for any variations | R | R | R | R |  |  | -Level 1 Project -Executing, Monitoring & Controlling -Project Change Request -Project Log -Risk Register
Manage project communications and stakeholder engagement | E | E | R | R |  |  | -Level 1 Project -Executing, Monitoring & Controlling -Project Change Request -Project Log -Communication Plan
Capture and communicate requested and approved changes | E | E | E | R |  |  | -Project Change Request -Project Log
Maintain the Project Log: -Review and update the Issues Log -Review and update the Risk Register -Review and update Action Items -Update the Change Log | R | R | R | R |  |  | -Executing, Monitoring & Controlling -Project Change Request -Project Log -Risk Register
Make necessary updates to the Project Plan | R | R | R | R |  |  | -Level 1 Project -Executing, Monitoring & Controlling -Project Change Request
For complex deployments, develop and execute a deployment plan that also addresses communication |  | E | R | R |  |  | -Executing, Monitoring & Controlling -Communication Plan
Obtain signoff on project deliverables | R | R | R | R |  |  | -Executing, Monitoring & Controlling -Project Change Request
Develop Closing templates Lessons Learned Report Post Project Survey | R | R | R | R |  |  | -Post Project Survey -Lessons Learned Report

## Closing
[5 empty] | Project: | <Project>
TAC 216 Checklist of Activities and Tasks that can be added to a project |  |  |  |  | Level: | 0
[5 empty] | R | A Required activity or task
[5 empty] | E | An Encouraged activity or task
Closing Requirements | Level 1 | Level 2 | Level 3 | Level 4 | Completed ( ) | If not, why not? | Related Templates
Obtain final acceptance of project completion | R | R | R | R
Close out the project
Deployment and transition to operations
Notify users | R | R | R | R |  |  | -Communication Plan
Develop end-user and operational documentation | R | R | R | R
Transfer knowledge to operational staff and service desk | R | R | R | R
Update information resources management system/configuration management database | E | E | R | R
Update Service Catalog/IT Services list and business processes | R | R | R | R
Establish product/service governance, if applicable | E | E | R | R
Release new products/services | R | R | R | R
Stabilization
Identify and address any open issues on the project | R | R | R | R |  |  | -Project Log
Finalize project backing | E | R | R | R |  |  | -Communication Plan
Close out procurement relationship
Finalize any open claims | R | R | R | R
Update records to reflect final results | R | R | R | R
Evaluate and document vendor performance | R | R | R | R
Conduct lessons learned for continuous improvement | [6 empty] | -Post Project Survey -Lessons Learned Report
Complete Compliance Validation Check list | R | R | R | R |  |  | -Level 1 Project -Project Closure
Project management processes | E | R | R | R
Change management processes | E | R | R | R |  |  | -Project Plan -Project Log
Product/service development processes | E | R | R | R |  |  | -Project Plan
Archive project documents (See AppendiR D - Project Document Management) | R | R | R | R