## Alternate Project Classificatio
Complexity Assessment Additional Guidelines
Use these guidelines with the Complexity Assessment score to help determine the project level.
| Level 1 Project | Level 2 Project | Level 3 Project | Level 4 Project
Effort for All Stakeholders (OIT and non OIT) | < 120 hours | < 360 hours | >= 360 hours | Not specified
| 1 person working 3, 40-hour weeks | 3 people working 3, 40-hour weeks
Core Project Team Size | 1 - 2 | 3 - 5 | >= 6 | Not specified
Overall Duration | 3 - 4 months | 5 - 7 months | 8 months - 1 year | > 1 year
Software, Hardware and Vendor Expense | No Bid or < $50K | Informal Bid & < $100K | Formal Bid & >= $100K | > $250K

## Complexity Assessment
Complexity Assessment |  |  |  |  | Task
Level 1
<Project Name> |  |  |  |  | Level 2
TAC 216 Companion Guide Version: |  |  |  |  | Level 3
Document Version: |  |  |  |  | Level 4
Date Completed:
Completed by:
Project managers should thoroughly evaluate a project's potential risks and understand the project's complexity before starting it. This evaluation also helps identify issues before they can affect the project's successful completion. Use this Complexity Assessment to help you systematically evaluate the risks and complexities of this project.
Scope
Defining what is required is not always easy. Clearly defined deliverables, objectives, and scope minimize project risk. Evaluate and assess all scope risks, whether quantifiable or not.
How well are project scope and requirements defined? |  | Score | Notes
Clearly defined | 1
Some ambiguity | 5
Vague or undefined | 10
Schedule
Keeping to timelines and agreed critical paths is one of the most difficult situations that project managers face. Evaluate scheduling issues that may trigger a project risk.
What is the estimated time it will take to reach operations status? |  | Score | Notes
3 months or less | 5
3 months - 1 year | 10
1 year or more | 20
Is there an internally or externally mandated deadline? |  | Score | Notes
No mandated deadline | 1
Internally mandated deadline | 5
Externally mandated deadline | 10
Budget
Accounting for the full cost of a project (e.g., materials, labor, vendors) provides a framework for ROI and insight into potential risks and associated project complexities. Consider all budget factors (including labor costs) that are needed for this project.
What is the total estimated cost, including the payroll cost of those working on the project? |  | Score | Notes
<$XXX> or less | 5
<$XXX> - <$XXX> | 10
<$XXX> or greater | 20
Quality
Failing to deliver quality can negatively affect customer satisfaction and create unplanned expenses to fix or redo unsatisfactory work. Evaluate potential quality risks and complexities before beginning the project.
How well defined are project team roles and responsibilities? |  | Score | Notes
Well defined roles and responsibilities | 1
Partially defined roles and responsibilities | 10
Undefined roles and responsibilities | 20
How available is the project team to work this project? |  | Score | Notes
Dedicated team available; minimal disruptions expected | 1
Partially dedicated or limited team; some disruptions expected | 5
Ad hoc or no clear team available; significant disruptions expected | 10
How knowledgeable is the project team with this type of project and/or the technology that will be used? |  | Score | Notes
Extensive knowledge and experience with this type of project or technology | 1
Some experience with this type of project or technology | 5
Little or no experience with this type of project or technology | 10
How involved are stakeholders? |  | Score | Notes
They define requirements, provide input to the schedule and accept deliverables | 1
Some input from surveys and they conduct final delivery testing | 10
No involvement or resistant to the project | 20
Organizational Impact
By definition, a project creates new and unique products or services which can impact processes or business units. Carefully evaluate the potential impact of this project on organizations and established processes.
How will this project impact current business processes? |  | Score | Notes
No change to business processes or work methods | 1
Some change to business processes or work methods | 10
Significant change to business processes or work methods | 20
How many end users must do part of their job differently? |  | Score | Notes
50 or fewer | 5
51 - 100 | 10
> 100 | 20
Other Risk Considerations
Assess the project against the following categories important to A&M System members.
Other Risks (Score all that apply) |  | Score | Notes
Includes managed data (FERPA, HIPAA, PCI, etc.) | 10
Impacts other systems or services | 10
Vendor responsible for critical deliverables | 10
Requires staff augmentation | 10
Has high visibility | 10
Project Complexity and Risk Factor Category Scores
Clarity of Scope/Requirements | 0 | Project Team Knowledge |  | 0
Project Length | 0 | Stakeholder Involvement |  | 0
Project Deadline | 0 | Business Process Impact |  | 0
Estimated Cost | 0 | Employee Impact |  | 0
Project Team Roles/Responsibilities | 0 | Other Risks |  | 0
Project Team Availability | 0 | Total Point Value |  | 0
Overall Project Complexity and Risk Score
Task (22-34) |  | Level 3 Project (89-139)
Level 1 Project (35-49) |  | Level 4 Project (> 139)
Level 2 Project (50-88)
Review your Project Level against the Alternate Project Classification worksheet and adjust the level if needed
Level 3 and 4 Projects: Contact Internal Audit and ask how they want to be included in project updates