## Instructions
Instructions
This Risk Register can be used to assess and document risk on any project. It asks you to complete the following:
Risk Description: | Describe the event or situation that could have a positive or negative effect on the project if it happens.
Risk Assessment: | Determine how severely the risk could impact the project.
Impact: | Choose the value that represents the risk's impact, where Low=1 and High=5.
Probability: | Determine the likelihood or chance that the risk will occur, where Low=1 and High =5.
Risk Score: | Multiply the Impact and Probability to Score the risk.
Impact To: | Indicate whether the risk impacts the project's scope, schedule, or budget.
Impact Details: | Optional: Provide additional detail about how the risk impacts the project.
Risk Owner: | Identify who is responsible for managing the risk.
Risk Response: | Describe one or more actions you can take to address the risk if it happens.
Using the Risk Register
The risk register should be managed by the project manager and re-evaluated and updated at regular intervals.
1. Identify project risks. - Make a list of everything that could impact the project what could cause it to happen. - Fill out the Risk # and Risk Description columns.
2. Assess the risk's severity. - Score the risk's Impact and Probability. Ask yourself the following: What is the impact of each risk on the overall project and how serious would it be? What is the probability or chance of the risk happening? - The Risk Register will multiply the Impact and Probability to find the Risk Score.
3. Indicate how the project is impacted by the risk. - Indicate if the risk impacts the project's scope, schedule or budget in the Impact To column. - Add detail about the impact (if needed) in the Impact Detail column.
4. Identify who will manage the risk. Choose a risk response. - Identify the Risk Owner. - Decide what actions need to be taken throughout the life of the project to reduce or eliminate the impact of the risk and enter them in the Risk Response column.
5. Decide how often the risk needs to be monitored and reviewed. - Using the Risk Score, decide how often the risk needs to be monitored and add that action to your project plan.

## Risk Register
University Copier Replacements
- Monitor LOW scores Quarterly (risk has <33% chance of happening). - Monitor MEDIUM scores Monthly (risk has 33% - 66% chance of happening). - Monitor HIGH scores Weekly or Daily, depending on project impact (risk has >66% chance of happening). | [6 empty] | Risk Matrix
Risk Score
Low 1 - 4 | Green indicates the risk level is low. The risk is not expected to impact other project metrics or overall project outcomes.
Med 5 - 9 | Yellow indicates some action or intervention may be needed. One or more risks may impact other project metrics or overall project outcomes.
High 10 - 25 | Red indicates significant action or intervention may be needed. One or more risks may impact other project metrics and overall project outcomes.
Risk Register
Risk # | Risk Description | Risk Assessment |  |  | Impact To: | Impact Details | Risk Owner | Risk Response
|  | Impact (I) | Probability (P) | Risk Score (I*P)
R0001 | If IT staff is unable to work on this project because of competing projects, the implementation date may be delayed. | 3 | 5 | 15 |  | Milestone will be or has been missed | Frank Sanchez | 1) Identify the critical path 2) Monitor progress on the critical path 3) Identify alternate resource availability 4) If the priority of this project decreases, re-estimate milestones and submit a Project Change Request to re-baseline milestones
R0002 | If all Stakeholders are not identified, the scope of the project could be incomplete | 5 | 3 | 15 |  | Initial Stakeholders have been identified | Tara Malish | 1) Project Initiation should include querying identified stakeholders for other impacted areas 2) Follow up with other impacted areas to determine if they need to be stakeholders for the project 3) Finalize the Stakeholder list as part of the Project Charter sign-off.
R0003 | If documentation of the current processes does not exist, the process will need to be documented before the project requirements can be finalized and this will delay the project | 5 | 5 | 25 |  | Determination that documentation does not exist or is insufficient. | Frank Sanchez | 1) Ask if Project documentation exists 2) If it does exist, review it for sufficiency 3) Convey to the group that this could delay the go-live date 4) Identify key process owners and define the processes that need to be documented 5) Concurrently write up requirements to minimize the impact to the go-live date
R0004 | If missed requirements are identified AFTER the Scope has been finalized in Design, the impact to the project will need to be assessed. | 3 | 3 | 9 |  | A missed requirement is identified | Frank Sanchez | 1) When Risk Trigger occurs, begin a Project Change Request to document the impacts of having or not having the missed requirement included in the project 2) Work with Stakeholders to determine if and when the missed requirement will be included in the project 3) Get Stakeholder sign-off on the decision
R0005 | If funding is not approved and encumbered before the project begins the project go-live will be delayed or on hold until the funding is encumbered. | 3 | 4 | 12 |  | Vendor Quote is received | Frank Sanchez | 1) Contact Business Office to find out if funds have been encumbered or the PO has been established 2) If PO has not been established contact the Project Sponsor to resolve the issue (Meet with Project Sponsor & Business Office) 3) Follow up to ensure that PO is issued
R0006 | If training is not available for Functional Users, user adoption will be minimal and they will perceive the application is not working. | 3 | 3 | 9 |  | During User Acceptance Testing, Functional Users are unable to complete Test Cases without assistance | Tara Malish | 1) Identify training needs, by Functional User group 2) Identify available training materials 3) Identify training or method for delivering training 4) Engage Project Sponsor to require training participation 5) Schedule training for Functional User groups
R0007 | If milestones or key project tasks are scheduled to occur during peak Functional User activity, participation will be limited, at best | 3 | 1 | 3 |  | Functional Users are not available during key Project Activity times | Patricia Philipps | 1) With initial Project constraints, identify dates when Functional Users will not be available to participate 2) Plan schedule to work around these dates 3) Plan key Functional User activities to occur during off-peak times
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget
Scope
Schedule
Budget